## Sheet1
Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Created | Due | Fix Version/s | Product Backlog
DSP001 | I want to be able create a databse for storing data | create a database using microsoft sql for storing data | Satwik | Vishal | Present | Completed | resolved | 2023-03-02 | 2023-03-03 | 1 | Database intsallation
DSP002 | I want to be able to link the databasre to the html pages | link the microsoft sql server to application | Satwik | Vishal | Present | Completed | resolved | 2023-03-03 | 2023-03-05 | 1 | database Linking
DSP003 | I want to able to create a login html page | create basic login page using html and php | Satwik | Vishal | Present | Completed | resolved | 2023-03-05 | 2023-03-07 | 1 | Login
DSP004 | I want to be able to log in to the application using my credentials | complete the login option | Satwik | Vishal | Present | In Progress | resolved | 2023-03-07 | 2023-03-09 | 1 | Login
DSP005 | I want to be able to sign up to the application | implement the sign up option | vimal | Vishal | Present | In Progress | Unresolved | 2023-03-09 | 2023-03-11 | 1 | Sign up
DSP006 | I want to able to reset the password | at login page made a password reset option | Vamsi | Vishal | Present | In Progress | Unresolved | 2023-03-11 | 2023-03-15 | 1 | password reset
DSP007 | I want to able to update my account details | implement the update option for account details | Satwik | Vishal | Present | In Progress | Unresolved | 2023-03-15 | 2023-03-19 | 1 | update details of user
DSP008 | I want to able view the user details | retrive the user details from database | Vamsi | Vishal | Present | In Progress | Unresolved | 2023-03-19 | 2023-03-23 | 1 | show the details of user
DSP009 | I want to able to show account details | retrive the Account details from database | Vimal | Vishal | Present | In Progress | Unresolved | 2023-03-23 | 2023-03-26 | 1 | Account details of user
DSP010 | I want to be able to Develop a homepage for the application | create a new html page for home page | Vamsi | Vishal | Present | Completed | Unresolved | 2023-03-26 | 2023-03-29 | 1 | Home page creation
DSP011 | I want to be able to user can create new bank account | implement a bank account create option | Vimal | Vishal | Present | In Progress | Unresolved | 2023-03-01 | 2023-03-03 | 1 | Create new bank account
DSP012 | I want to be able to create web page for loan apply | implement a form filling web for loan application | Satwik | Vishal | Present | In Progress | Unresolved | 2023-03-03 | 2023-03-08 | 1 | Loan application
DSP013 | I want to be able to user can apply for his loan | implement a loan application form | Vamsi | Vishal | Present | Not started | Unresolved | 2023-03-08 | 2023-03-11 | 1 | Loan application
DSP014 | I want to be able to send money to another user | implement the transaction option from user to user | Vamsi | Vishal | Present | Not started | Unresolved | 2023-03-11 | 2023-03-17 | 1 | Transaction
DSP015 | I want to select the recipent to receive money | implement the recipent account selection | vamsi | vishal | Present | completed | resolved | 2023-03-17 | 2023-03-20 | 1 | Transaction
DSP016 | I want to able to make a payment option | implement the make a payment option | Satwik | vishal | Present | completed | resolved | 2023-03-20 | 2023-02-23 | 1 | Transaction
DSP017 | I want to do Mobile reacharge through make a payment option | create a option to make reacharge using account number | Satwik | vishal | present | completed | resolved | 2023-03-23 | 2023-03-26 | 1 | Transaction
DSP018 | I want to do fastag through make a payment option | create a option to make fsatag reacharge using account number | vimal | vishal | present | Completed | resolved | 2023-03-26 | 2023-03-30 | 1 | Transaction
DSP019 | I want to do televison recahrge through make a payment option | create a option to make television top up using account number | vimal | vishal | present | Completed | resolved | 2023-03-30 | 2023-04-04 | 1 | Transaction
DSP020 | I want to able sto show the transaction details (debited) | retrive the payement transaction from database | vimal | vishal | present | In Progress | Unresolved | 2023-04-04 | 2023-04-08 | 1 | Transaction History
DSP021 | I want to able sto show the transaction details (credited) | retrive the payement transaction from database | Vamsi | vishal | presnet | completed | resolved | 2023-04-08 | 2023-04-12 | 1 | Transaction History
DSP022 | I want to able see the additional details of history ( id, time ) | store the time in database when the transaction made and retrive | Vamsi | Vishal | Present | Completed | resolved | 2023-04-12 | 2023-04-16 | 1 | Transaction History
DSP023 | I want able to create a login page for employee | create html page for login | Satwik | Vishal | Present | Completed | resolved | 2023-04-16 | 2023-04-20 | 1 | Login
DSP024 | I want to able to create a sign up page for employee | create a html page for sign up | Vamsi | Vishal | Present | Completed | resolved | 2023-04-20 | 2023-04-24 | 1 | sign up
DSP025 | I want to connect employee table to database | Connect the databse | vimal | vishal | Present | Completed | resolved | 2023-04-24 | 2023-04-30 | 1 | database Linking
DSP026 | I want to able to show the profile managament | retrive the employee details from database | vimal | Vishal | Present | Completed | resolved | 2023-04-30 | 2023-05-04 | 1 | profile management
DSP027 | I want to able to edit the details of Employee | option to edit the details in database | Satwik | Vishal | Present | Completed | resolved | 2023-05-04 | 2023-05-08 | 1 | edit the details
DSP028 | I want able to employee to deposit cash in customer account | option to add money in customer account | Vamsi | Vishal | Present | Completed | resolved | 2023-05-08 | 2023-05-13 | 1 | Cash Deposit
DSP029 | I want able to show all the transaction made by bank | all the transaction made in that bank | Satwik | Vishal | Present | Completed | resolved | 2023-05-13 | 2023-05-17 | 1 | Transaction Details